## Tracker
NDMA — AI-Integrated Digital Twin Command Dashboard · Project Tracker
Source: NDMA_Digital_Twin_Proposal.pdf · Phase 1 = one pilot district, riverine flood · Phase 2 = landslide, cyclone, more sensor/crowd inputs · Phase 3 = multi-district scale-up · Edit Start, End and Status; Working days recalculates (weekends and the Holidays tab excluded). Dates are planned from dependencies starting 12 Oct 26.
Module | Category | Task | Sub Task | Description | Acceptance criteria / Definition of done | Start | End | Working days | Status | Dependency / Blocker | Comments | Artifacts
A – Programme Setup & Governance | 1. Project Initiation | Solution Proposal | Draft AI-integrated Digital Twin proposal | Write the solution proposal: problem statement, five-layer solution, dashboard features, usage example, data sources, risks and expected impact. | Done when: proposal (PDF + DOCX) is complete and committed to the repo. | 2026-09-21 | 2026-10-02 | 10 | Done |  |  | NDMA_Digital_Twin_Proposal.pdf; NDMA_Digital_Twin_Proposal (1).docx
|  |  | Proposal walkthrough and sign-off with NDMA | Present the proposal to NDMA, capture feedback and get written go-ahead for Phase 1. | Done when: NDMA sign-off (email/minutes) received and feedback logged. | 2026-10-12 | 2026-10-15 | 4 | Not Started | After: Draft AI-integrated Digital Twin proposal (P0). Needs: NDMA meeting slot for walkthrough.
|  | Scope & Pilot | Select Phase 1 pilot district | Pick one well-mapped, flood-prone district with CWC gauges, good DEM coverage and a willing DEOC (mitigates the terrain-resolution risk). | Done when: pilot district agreed in writing with a scored selection matrix. | 2026-10-16 | 2026-10-23 | 5 | Not Started | After: Proposal walkthrough and sign-off with NDMA (P1). Needs: NDMA / State SDMA nomination of candidate districts.
|  |  | Lock Phase 1 hazard and scope | Phase 1 = riverine flood in the pilot district. Landslide, cyclone and wider sensor/crowd inputs move to Phase 2; multi-district scale-up is Phase 3. | Done when: in/out-of-scope list signed off by NDMA. | 2026-10-26 | 2026-10-28 | 3 | Not Started | After: Select Phase 1 pilot district (P2).
|  |  | User roles and operational workflows | Interview NDMA, SEOC, DEOC and NDRF/SDRF users; map how they plan shelters, routes and deployments today. | Done when: personas, current-vs-future workflow maps and a prioritised needs list are documented. | 2026-10-16 | 2026-10-26 | 6 | Not Started | After: Proposal walkthrough and sign-off with NDMA (P1).
|  |  | Success metrics and acceptance bar | Agree measurable targets: flood-extent accuracy (IoU/CSI), forecast lead time, route recompute time, dashboard load time. | Done when: metric targets are agreed with NDMA and referenced by validation tasks. | 2026-10-29 | 2026-11-03 | 4 | Not Started | After: Lock Phase 1 hazard and scope (P3); User roles and operational workflows (P4).
| 2. Data Agreements & Governance | Data-Sharing Agreements | IMD data-sharing agreement | Formal agreement for rainfall nowcasts, district forecasts and cyclone bulletins (API/FTP access). | Done when: signed agreement and working credentials/endpoint for the pilot district. | 2026-10-26 | 2026-11-20 | 20 | Not Started | After: Select Phase 1 pilot district (P2). Needs: IMD nodal officer; NDMA letter of request.
|  |  | CWC data-sharing agreement | Agreement for real-time river gauge levels and flood forecasts. | Done when: signed agreement and live gauge feed access for pilot basins. | 2026-10-26 | 2026-11-20 | 20 | Not Started | After: Select Phase 1 pilot district (P2). Needs: CWC nodal officer; NDMA letter of request.
|  |  | ISRO / NRSC satellite data access | Access to optical and SAR imagery and flood maps (Bhuvan / NDEM) for the pilot district. | Done when: imagery access confirmed and a sample scene downloaded. | 2026-10-26 | 2026-11-27 | 25 | Not Started | After: Select Phase 1 pilot district (P2). Needs: NRSC approval via NDMA.
|  |  | Survey of India high-resolution DEM licence | Licence for high-resolution elevation data — the base terrain of the 3D twin. | Done when: licence signed and DEM tiles for the pilot district received. | 2026-10-26 | 2026-11-20 | 20 | Not Started | After: Select Phase 1 pilot district (P2). Needs: SoI licence approval.
|  |  | Census / LGD data access | Population, household and administrative boundary data for impact and shelter sizing. | Done when: ward/village-level population and LGD boundaries for the pilot district are available. | 2026-10-26 | 2026-11-06 | 10 | Not Started | After: Select Phase 1 pilot district (P2).
|  |  | Google Maps Platform licence and billing | Enable Roads, Places and Traffic APIs with a government billing account and usage caps. | Done when: API keys issued with quotas and a cost estimate approved. | 2026-10-16 | 2026-10-28 | 8 | Not Started | After: Proposal walkthrough and sign-off with NDMA (P1). Needs: budget approval for API usage.
|  |  | Commercial high-resolution imagery procurement | Procure fine-resolution imagery for the pilot district to sharpen terrain and infrastructure detail. | Done when: purchase order issued and imagery delivered. | 2026-10-26 | 2026-12-04 | 30 | Not Started | After: Select Phase 1 pilot district (P2). Needs: procurement approval (GeM). | Pilot district only in Phase 1.
|  | Privacy & Data Governance | Data governance and privacy policy | Policy covering citizen location/photo data and social media signals under the DPDP Act 2023: purpose limitation, minimisation, retention, access. | Done when: policy approved by NDMA legal and published internally. | 2026-10-16 | 2026-11-06 | 15 | Not Started | After: Proposal walkthrough and sign-off with NDMA (P1). Needs: NDMA legal review. | Runs alongside the technical build (proposal risk: data privacy & consent).
|  |  | Data classification and retention rules | Classify each data source (public / restricted / personal) and set retention periods. | Done when: every ingested source has a class and retention rule applied in the pipeline config. | 2026-11-09 | 2026-11-13 | 5 | Not Started | After: Data governance and privacy policy (G1).
|  |  | Consent flow for citizen ground reports | Consent text and opt-in flow for WhatsApp / SACHET reports (photo + location). | Done when: consent text approved and recorded with every citizen report. | 2026-11-09 | 2026-11-13 | 5 | Not Started | After: Data governance and privacy policy (G1).
B – Unified Data Ingestion (Layer 1) | 3. Ingestion Foundation | Common Data Model | Canonical schema for all feeds | One schema for every source: timestamp (UTC + IST), geometry, source, unit, confidence and raw-payload reference. | Done when: schema documented and validated against samples from every Phase 1 source. | 2026-10-29 | 2026-11-09 | 8 | Not Started | After: Lock Phase 1 hazard and scope (P3).
|  | Ingestion Framework | Connector framework and scheduler | Reusable connector framework with scheduling, retries, back-fill and idempotent loads so feeds stay fresh without manual effort. | Done when: scheduled runs complete, resume after interruption and never run twice at once. | 2026-11-10 | 2026-11-23 | 10 | Not Started | After: Canonical schema for all feeds (I1); Dev / test / prod environments as code (H1).
|  |  | Spatial data store (PostGIS + object storage) | Store vector layers, time-series and rasters/imagery in one spatially indexed store. | Done when: store is provisioned in dev/test with spatial indexes and backup. | 2026-11-10 | 2026-11-19 | 8 | Not Started | After: Canonical schema for all feeds (I1); Dev / test / prod environments as code (H1).
|  |  | Pipeline status view (last run, errors, owner) | Simple view showing, per source, when it last succeeded, what failed and who owns it. | Done when: operations can spot a stale/failed feed without engineering help. | 2026-11-24 | 2026-11-30 | 5 | Not Started | After: Connector framework and scheduler (I2).
| 4. Agency Feeds | IMD | IMD connector (rainfall, forecasts, cyclone bulletins) | Pull nowcasts, district rainfall forecasts and bulletins into the canonical schema. | Done when: IMD data for the pilot district lands every cycle with < 1 cycle lag. | 2026-11-24 | 2026-12-03 | 8 | Not Started | After: Connector framework and scheduler (I2); IMD data-sharing agreement (D1).
|  | CWC | CWC connector (gauge levels, flood forecasts) | Pull river gauge levels, danger/warning marks and flood forecasts for the pilot basins. | Done when: all pilot-basin gauges update on schedule with danger marks attached. | 2026-11-24 | 2026-12-03 | 8 | Not Started | After: Connector framework and scheduler (I2); CWC data-sharing agreement (D2).
|  | ISRO / NRSC | Satellite imagery connector (optical + SAR) | Ingest optical and SAR scenes and NRSC flood-extent products for change detection. | Done when: new scenes for the pilot district are catalogued automatically. | 2026-11-30 | 2026-12-11 | 10 | Not Started | After: Connector framework and scheduler (I2); ISRO / NRSC satellite data access (D3).
|  | Open Satellite | Copernicus Sentinel-1/2 and Landsat connector | Open imagery for flood-extent and land-cover validation (no agreement needed). | Done when: scenes over the pilot district are searchable by date and cloud cover. | 2026-11-24 | 2026-12-03 | 8 | Not Started | After: Connector framework and scheduler (I2).
| 5. Static & Reference Layers | Terrain | Ingest and tile SoI DEM | Clean, reproject and tile the DEM; fill voids from open DEMs where needed. | Done when: seamless DEM for the pilot district is served as tiles with void report. | 2026-11-23 | 2026-11-30 | 6 | Not Started | After: Spatial data store (PostGIS + object storage) (I3); Survey of India high-resolution DEM licence (D4).
|  | Population & Boundaries | Census / LGD population and boundaries | Load ward/village boundaries and population, households and age bands. | Done when: every zone in the pilot district has population and household counts. | 2026-11-20 | 2026-11-27 | 6 | Not Started | After: Spatial data store (PostGIS + object storage) (I3); Census / LGD data access (D5).
|  | Infrastructure | Roads, bridges and critical facilities layer | Build roads, bridges, hospitals, schools and govt buildings from OSM + Google Places/Roads. | Done when: routable road network and facility layer cover the pilot district. | 2026-11-20 | 2026-12-01 | 8 | Not Started | After: Spatial data store (PostGIS + object storage) (I3); Google Maps Platform licence and billing (D6).
|  | History | Historical disaster records | Collect past flood events: dates, gauge peaks, mapped extents, damage and relief records. | Done when: at least 5 past flood events are catalogued with extents for backtesting. | 2026-11-20 | 2026-12-03 | 10 | Not Started | After: Spatial data store (PostGIS + object storage) (I3). | Used to calibrate and backtest every model.
|  | Resources | IDRN resource inventory import | Import India Disaster Resource Network equipment and team inventory for the pilot state. | Done when: IDRN inventory is queryable by location and resource type. | 2026-11-20 | 2026-11-26 | 5 | Not Started | After: Spatial data store (PostGIS + object storage) (I3). Needs: IDRN data access via NDMA.
| 6. Sensor & Crowdsourced Feeds | Hardware Sensors | River / rain gauge sensor telemetry (pilot) | Ingest telemetry from pilot river-level and rainfall gauges (MQTT/HTTP). | Done when: pilot sensors stream into the store with device health status. | 2026-11-24 | 2026-12-07 | 10 | Not Started | After: Connector framework and scheduler (I2). Needs: sensor vendor / state agency feed access.
|  | Ground Reporting | WhatsApp ground-reporting bot | Structured bot for field staff and citizens to send photo + location + short description. | Done when: reports arrive geotagged with consent recorded and reach the ingestion layer. | 2026-11-24 | 2026-12-09 | 12 | Not Started | After: Connector framework and scheduler (I2); Consent flow for citizen ground reports (G3). Needs: WhatsApp Business API account.
|  |  | Report verification and trust score | De-duplicate, geo-check and score reports (image checks, reporter history, agreement with sensors) before they are trusted. | Done when: every report carries a trust score and low-trust reports are held for review. | 2026-12-10 | 2026-12-23 | 10 | Not Started | After: WhatsApp ground-reporting bot (I17). | Mitigation for crowdsourced misinformation risk.
| 7. Data Quality | Normalisation | Units, CRS and time-zone normalisation | Convert all feeds to common units, one CRS and UTC/IST timestamps. | Done when: no unit/CRS mismatches across Phase 1 sources in the QA report. | 2026-12-04 | 2026-12-10 | 5 | Not Started | After: IMD connector (rainfall, forecasts, cyclone bulletins) (I5); CWC connector (gauge levels, flood forecasts) (I6).
|  | Quality Rules | Staleness, gap and outlier rules with alerts | Rules that flag stale feeds, missing values and impossible readings; alert the data owner. | Done when: rules are documented, applied and alerts fire in test. | 2026-12-11 | 2026-12-18 | 6 | Not Started | After: Units, CRS and time-zone normalisation (I21).
C – AI/ML Prediction Engine (Layer 2) | 8. EDA & Feature Prep | EDA | EDA on historical floods, rainfall and gauges | Study rainfall–gauge lag, upstream/downstream relationships and past extents in the pilot basin. | Done when: findings and modelling decisions are documented in a notebook. | 2026-12-04 | 2026-12-15 | 8 | Not Started | After: Historical disaster records (I12); CWC connector (gauge levels, flood forecasts) (I6); IMD connector (rainfall, forecasts, cyclone bulletins) (I5).
|  | Features | Feature store (rainfall accumulations, upstream levels, soil, land cover) | Reusable, versioned features for all flood models. | Done when: features are reproducible from raw data with one command. | 2026-12-21 | 2026-12-31 | 8 | Not Started | After: EDA on historical floods, rainfall and gauges (M1); Staleness, gap and outlier rules with alerts (I22).
| 9. Flood Forecasting | Hydraulic Model | Hydraulic/hydrological model set-up on DEM | Set up a physics model (e.g. HEC-RAS 2D / LISFLOOD-FP) for the pilot basin and calibrate on past events. | Done when: model reproduces at least 3 historical extents within the agreed accuracy bar. | 2026-12-16 | 2027-01-06 | 15 | Not Started | After: Ingest and tile SoI DEM (I9); EDA on historical floods, rainfall and gauges (M1).
|  | ML Forecaster | Gauge-level forecaster (6/12/24/48 h) | ML model (e.g. LSTM / gradient boosting) forecasting gauge levels from rainfall and upstream levels. | Done when: beats CWC persistence baseline on held-out seasons. | 2027-01-01 | 2027-01-21 | 15 | Not Started | After: Feature store (rainfall accumulations, upstream levels, soil, land cover) (M2).
|  | Flood Extent | Flood-extent prediction (hydraulic + ML surrogate) | Fast surrogate of the hydraulic model driven by forecast levels to produce extents in minutes. | Done when: surrogate extents match the full model within the agreed tolerance and run in < 5 min. | 2027-01-22 | 2027-02-12 | 15 | Not Started | After: Hydraulic/hydrological model set-up on DEM (M3); Gauge-level forecaster (6/12/24/48 h) (M4).
|  | Fusion | Fuse IMD, CWC and ISRO signals into one forecast | Combine agency forecasts, sensor data and satellite-observed extents into one localised forecast. | Done when: one fused forecast is produced per cycle with source contributions logged. | 2027-02-15 | 2027-02-26 | 10 | Not Started | After: Flood-extent prediction (hydraulic + ML surrogate) (M5); Satellite imagery connector (optical + SAR) (I7); River / rain gauge sensor telemetry (pilot) (I14).
| 10. Risk Scoring | Zone Risk | Per-zone risk score | Continuously updated risk score per zone (ward / hex grid) combining hazard and exposure. | Done when: every zone has a score refreshed each forecast cycle. | 2027-03-01 | 2027-03-10 | 8 | Not Started | After: Fuse IMD, CWC and ISRO signals into one forecast (M6); Census / LGD population and boundaries (I10).
|  | Time-Boxed Forecast | Hour-by-hour hazard extents | Time-boxed forecasts (e.g. extent X by hour 18, Y by hour 24) instead of static labels. | Done when: hourly extents for the forecast window are published per cycle. | 2027-03-11 | 2027-03-18 | 6 | Not Started | After: Per-zone risk score (M7).
|  | Uncertainty | Confidence bands for extents and scores | Show likely / worst-case extents and a confidence level so operators know how far to trust each forecast. | Done when: every forecast carries a confidence band and calibration is checked. | 2027-03-19 | 2027-03-29 | 6 | Not Started | After: Hour-by-hour hazard extents (M8).
|  | Thresholds | Critical-threshold and alert rules | Rules that raise alerts and trigger pre-positioning when a zone crosses a critical score. | Done when: thresholds are agreed with NDMA and alerts fire correctly in replay. | 2027-03-30 | 2027-04-02 | 4 | Not Started | After: Confidence bands for extents and scores (M9); Success metrics and acceptance bar (P5).
| 11. Model Validation | Backtesting | Backtest against historical events | Replay past floods end to end and compare predicted vs observed extents, timings and gauges. | Done when: backtest report meets the agreed acceptance bar for all catalogued events. | 2027-03-19 | 2027-04-02 | 10 | Not Started | After: Hour-by-hour hazard extents (M8); Historical disaster records (I12). | Mitigation for model-trust risk.
|  | Reporting | Model card and accuracy report | Plain-language model card: data, method, accuracy by zone, known weaknesses. | Done when: reviewed and accepted by NDMA technical committee. | 2027-04-05 | 2027-04-08 | 4 | Not Started | After: Backtest against historical events (M11).
D – Digital Twin Simulation (Layer 3) | 12. 3D Base Twin | Engine | 3D engine selection and spike | Compare CesiumJS, deck.gl and similar for terrain, 3D tiles, time animation and offline support. | Done when: engine chosen with a working spike on pilot terrain. | 2026-10-29 | 2026-11-04 | 5 | Not Started | After: Lock Phase 1 hazard and scope (P3).
|  | Terrain | Terrain mesh from DEM (3D tiles) | Convert the DEM into streamable 3D terrain tiles. | Done when: pilot district terrain loads smoothly in the browser. | 2026-12-01 | 2026-12-10 | 8 | Not Started | After: 3D engine selection and spike (T1); Ingest and tile SoI DEM (I9).
|  | Infrastructure | Buildings and infrastructure 3D layer | Extrude buildings and add roads, bridges and critical facilities to the twin. | Done when: critical facilities and road network are visible and selectable. | 2026-12-11 | 2026-12-24 | 10 | Not Started | After: Terrain mesh from DEM (3D tiles) (T2); Roads, bridges and critical facilities layer (I11).
|  | Imagery | Satellite imagery drape | Drape latest optical imagery (open + commercial) over terrain. | Done when: imagery layer can be switched by date. | 2026-12-11 | 2026-12-17 | 5 | Not Started | After: Terrain mesh from DEM (3D tiles) (T2); Copernicus Sentinel-1/2 and Landsat connector (I8).
| 13. Hazard Simulation | Animation | Animated flood spread over forecast window | Render forecast extents and depths as an animated layer on the twin. | Done when: the twin animates predicted spread hour by hour for any forecast cycle. | 2027-03-19 | 2027-04-02 | 10 | Not Started | After: Buildings and infrastructure 3D layer (T3); Hour-by-hour hazard extents (M8).
|  | Timeline | Timeline scrubber (rewind / fast-forward) | Rotate, zoom and scrub through the forecast timeline. | Done when: operators can jump to any forecast hour in < 2 s. | 2027-04-05 | 2027-04-12 | 6 | Not Started | After: Animated flood spread over forecast window (T5).
|  | Impact View | Cut-off roads and threatened neighbourhoods | Highlight roads predicted to flood and neighbourhoods at risk, readable by non-technical users. | Done when: cut-off roads and threatened areas are highlighted per forecast hour. | 2027-04-05 | 2027-04-12 | 6 | Not Started | After: Animated flood spread over forecast window (T5); Roads, bridges and critical facilities layer (I11).
|  | Performance | Performance on SEOC / district hardware | Optimise tiles and rendering for typical control-room machines and bandwidth. | Done when: first load < 5 s and smooth playback on agreed reference hardware. | 2027-04-13 | 2027-04-19 | 5 | Not Started | After: Timeline scrubber (rewind / fast-forward) (T6).
| 14. Shadow Mode | Replay | Replay historical events in the twin | Run the twin against past floods to validate behaviour before live use. | Done when: any catalogued historical event can be replayed end to end. | 2027-04-13 | 2027-04-22 | 8 | Not Started | After: Timeline scrubber (rewind / fast-forward) (T6); Backtest against historical events (M11).
|  | Comparison | Predicted vs observed side-by-side | Overlay observed extents (satellite) on predicted extents with an error summary. | Done when: side-by-side view and error summary are available for every replayed event. | 2027-04-23 | 2027-04-30 | 6 | Not Started | After: Replay historical events in the twin (T9).
E – Planning & Decision Support (Layer 4) | 15. Impact & Affected-Area Analysis | Affected Population | Affected population and households per zone | Overlay Census/LGD population on hazard extents to estimate people and households affected. | Done when: per-zone affected counts are produced for every forecast hour. | 2027-03-11 | 2027-03-22 | 8 | Not Started | After: Per-zone risk score (M7); Census / LGD population and boundaries (I10).
|  | Infrastructure | Critical infrastructure exposure | List hospitals, schools, bridges, substations etc. inside predicted extents. | Done when: exposed assets are listed per zone and hour. | 2027-03-23 | 2027-03-31 | 6 | Not Started | After: Affected population and households per zone (E1); Roads, bridges and critical facilities layer (I11).
|  | Projections | Time-boxed impact projections | Impact numbers by hour (e.g. 'X households by hour 18, Y by hour 24'). | Done when: projections refresh automatically with each forecast cycle. | 2027-03-23 | 2027-03-30 | 5 | Not Started | After: Affected population and households per zone (E1); Hour-by-hour hazard extents (M8).
|  | Vulnerability | Vulnerable-pocket flagging | Flag high-risk zones with vulnerable groups (e.g. elderly) lacking nearby heavy-equipment teams via IDRN. | Done when: vulnerable pockets are flagged with the reason shown. | 2027-04-01 | 2027-04-12 | 8 | Not Started | After: Critical infrastructure exposure (E2); IDRN resource inventory import (I13).
| 16. Shelter & Safe-House Planning | Shelter Candidates | Candidate shelters outside the hazard zone | Identify schools, community halls and govt buildings (Places/POI + local lists) outside predicted extents. | Done when: candidate list updates with each forecast and excludes sites inside the extent. | 2027-03-23 | 2027-04-02 | 8 | Not Started | After: Affected population and households per zone (E1); Roads, bridges and critical facilities layer (I11).
|  |  | Shelter suitability scoring | Score candidates on capacity, access route safety, distance and facilities. | Done when: ranked shortlist is produced per affected zone. | 2027-04-05 | 2027-04-12 | 6 | Not Started | After: Candidate shelters outside the hazard zone (E5).
|  | Capacity | Live shelter capacity tracking | Track occupancy so operators see which shelters are filling up. | Done when: occupancy can be updated by field staff and shows on the dashboard. | 2027-04-13 | 2027-04-22 | 8 | Not Started | After: Shelter suitability scoring (E6).
|  |  | Shelter demand vs capacity gap | Compare projected displaced population with available capacity by zone and hour. | Done when: gaps are flagged with suggested extra sites. | 2027-04-23 | 2027-04-29 | 5 | Not Started | After: Live shelter capacity tracking (E7); Time-boxed impact projections (E3).
| 17. Evacuation Route Planning | Road Graph | Routable road graph with predicted closures | Mark road segments predicted to flood or close for each forecast hour. | Done when: graph reflects predicted closures per forecast hour. | 2027-03-19 | 2027-04-02 | 10 | Not Started | After: Roads, bridges and critical facilities layer (I11); Hour-by-hour hazard extents (M8).
|  | Routing | Safe evacuation route computation | Compute evacuation routes from affected zones to shelters avoiding predicted closures. | Done when: every affected zone has a safe route to its assigned shelter or is flagged as cut off. | 2027-04-13 | 2027-04-22 | 8 | Not Started | After: Routable road graph with predicted closures (E9); Shelter suitability scoring (E6).
|  |  | Relief-vehicle routing with live traffic | Routes for relief vehicles using Google Roads/Traffic plus predicted hazard. | Done when: relief routes include live traffic and avoid predicted closures. | 2027-04-23 | 2027-04-30 | 6 | Not Started | After: Safe evacuation route computation (E10); Google Maps Platform licence and billing (D6).
|  |  | Automatic recompute on forecast update | Recompute routes whenever the forecast changes so plans are always current. | Done when: routes refresh within 5 min of a new forecast. | 2027-04-23 | 2027-04-29 | 5 | Not Started | After: Safe evacuation route computation (E10).
|  | De-confliction | Citizen vs NDRF route conflict detection | Flag where citizen evacuation routes and NDRF relief routes collide. | Done when: conflicts are flagged with suggested alternatives. | 2027-05-03 | 2027-05-10 | 6 | Not Started | After: Relief-vehicle routing with live traffic (E11).
|  | Export | Export route and shelter plans for official channels | Operator-issued export for SACHET / Cell Broadcast. Nothing is sent automatically. | Done when: plans export in the agreed format after operator approval. | 2027-04-30 | 2027-05-05 | 4 | Not Started | After: Automatic recompute on forecast update (E12); Shelter demand vs capacity gap (E8). Needs: SACHET / C-DOT message format confirmation.
F – Force Coordination & Control (Layer 5) | 18. Force Tracking | Unit Registry | NDRF / SDRF unit and capability registry | Register units, capabilities, equipment and home bases. | Done when: all units for the pilot state are registered with capabilities. | 2026-11-27 | 2026-12-03 | 5 | Not Started | After: IDRN resource inventory import (I13). Needs: NDRF / SDRF unit data.
|  | Live Tracking | GPS / radio tracking integration | Plot responder positions from GPS devices or existing radio tracking. | Done when: live positions update on the map at the agreed interval. | 2026-12-04 | 2026-12-17 | 10 | Not Started | After: NDRF / SDRF unit and capability registry (F1). Needs: NDRF tracking feed access.
|  |  | Forces on the 3D twin | Show unit positions on the hazard simulation. | Done when: units appear on the twin with status and last-seen time. | 2027-04-13 | 2027-04-19 | 5 | Not Started | After: GPS / radio tracking integration (F2); Timeline scrubber (rewind / fast-forward) (T6).
| 19. Predictive Pre-positioning | Staging | Staging locations outside predicted zone | Choose staging points that remain outside the predicted extent and are reachable. | Done when: staging candidates stay valid across the whole forecast window. | 2027-04-05 | 2027-04-14 | 8 | Not Started | After: Critical-threshold and alert rules (M10); Candidate shelters outside the hazard zone (E5).
|  | Deployment Plans | Auto-generated deployment plan | When a zone crosses the critical threshold, recommend which units move, where and by when. | Done when: plans are generated within 5 min of a threshold crossing. | 2027-04-15 | 2027-04-28 | 10 | Not Started | After: Staging locations outside predicted zone (F4); NDRF / SDRF unit and capability registry (F1).
|  |  | ETA estimation | Estimated arrival times using hazard-aware routing. | Done when: every plan shows ETAs that account for predicted closures. | 2027-05-03 | 2027-05-07 | 5 | Not Started | After: Auto-generated deployment plan (F5); Relief-vehicle routing with live traffic (E11).
|  | Human in the Loop | Commander approval workflow | Commanders accept, edit or reject recommendations; all decisions are logged. | Done when: no recommendation is actioned without approval and every decision is audited. | 2027-04-29 | 2027-05-05 | 5 | Not Started | After: Auto-generated deployment plan (F5).
| 20. Unified Command View | SEOC Screen | Unified SEOC command screen | One screen with hazard zones, force deployments and ETAs, replacing radio check-ins. | Done when: SEOC staff can run a full scenario from this one screen. | 2027-05-10 | 2027-05-19 | 8 | Not Started | After: Forces on the 3D twin (F3); ETA estimation (F6); Commander approval workflow (F7); Shelter demand vs capacity gap (E8).
G – Command Dashboard & Feedback Loop | 21. Dashboard UX | UX Research | Wireframes from user workflows | Low-fidelity wireframes of all panels based on the workflow study. | Done when: wireframes are reviewed with NDMA and SEOC users. | 2026-10-27 | 2026-11-09 | 10 | Not Started | After: User roles and operational workflows (P4).
|  | Design | Design system and high-fidelity mockups | Visual design, colour scales for risk, accessibility and control-room (large screen) layouts. | Done when: mockups approved by NDMA. | 2026-11-10 | 2026-11-19 | 8 | Not Started | After: Wireframes from user workflows (U1).
| 22. Dashboard Build | Shell | Dashboard shell (login, layout, layer toggles) | Base app: SSO login, layout, map/twin container and layer controls. | Done when: shell is deployed in test with SSO. | 2026-11-20 | 2026-12-03 | 10 | Not Started | After: Design system and high-fidelity mockups (U2); 3D engine selection and spike (T1); SSO, role-based access and audit logs (H3).
|  |  | Role-based views (NDMA, SEOC, DEOC, NDRF) | Each role sees the panels and areas relevant to it. | Done when: each role sees only its permitted views and data. | 2026-12-04 | 2026-12-11 | 6 | Not Started | After: Dashboard shell (login, layout, layer toggles) (U3).
|  | Panels | Risk and alerts panel | Per-zone risk scores, threshold alerts and confidence. | Done when: alerts appear within one forecast cycle of a threshold crossing. | 2027-04-05 | 2027-04-12 | 6 | Not Started | After: Dashboard shell (login, layout, layer toggles) (U3); Critical-threshold and alert rules (M10).
|  |  | Impact panel | Affected population, households, infrastructure and vulnerable pockets. | Done when: panel matches the impact analysis outputs. | 2027-04-13 | 2027-04-19 | 5 | Not Started | After: Dashboard shell (login, layout, layer toggles) (U3); Vulnerable-pocket flagging (E4).
|  |  | Shelter panel | Shelter recommendations, live capacity and gaps. | Done when: operators can review, edit and lock a shelter plan. | 2027-04-30 | 2027-05-06 | 5 | Not Started | After: Dashboard shell (login, layout, layer toggles) (U3); Shelter demand vs capacity gap (E8).
|  |  | Route planning workspace | Evacuation and relief routes with conflicts and export. | Done when: operators can generate, compare and export route plans. | 2027-05-11 | 2027-05-18 | 6 | Not Started | After: Dashboard shell (login, layout, layer toggles) (U3); Citizen vs NDRF route conflict detection (E13); Export route and shelter plans for official channels (E14).
|  | Accessibility | English / Hindi interface | Bilingual labels and reports for district users. | Done when: all labels and exports are available in English and Hindi. | 2026-12-14 | 2026-12-17 | 4 | Not Started | After: Role-based views (NDMA, SEOC, DEOC, NDRF) (U4).
|  |  | Low-bandwidth mode for district EOCs | Lighter 2D fallback and cached tiles for poor connectivity. | Done when: dashboard is usable at the agreed low-bandwidth profile. | 2027-04-20 | 2027-04-27 | 6 | Not Started | After: Role-based views (NDMA, SEOC, DEOC, NDRF) (U4); Performance on SEOC / district hardware (T8).
| 23. Continuous Feedback | Feedback Loop | Ground reports update the forecast | Verified ground reports adjust the observed state and trigger a re-forecast. | Done when: a verified report changes the next forecast cycle and is traceable. | 2027-03-19 | 2027-03-31 | 8 | Not Started | After: Report verification and trust score (I20); Hour-by-hour hazard extents (M8).
|  |  | Sensor and force updates in near real time | Live sensor and force-position updates refresh forecast, routes and plans. | Done when: dashboard refreshes within the agreed latency after new data. | 2027-04-30 | 2027-05-11 | 8 | Not Started | After: Ground reports update the forecast (FB1); GPS / radio tracking integration (F2); Automatic recompute on forecast update (E12).
|  |  | Operator verification queue for reports | Queue where operators confirm or reject low-trust reports. | Done when: every low-trust report is reviewed or expires with a reason. | 2026-12-24 | 2026-12-31 | 5 | Not Started | After: Report verification and trust score (I20); Dashboard shell (login, layout, layer toggles) (U3).
H – Platform, Security & MLOps | 24. Infrastructure | Hosting | Hosting decision (MeghRaj / NIC / GovCloud) | Choose a government-approved cloud with data residency in India. | Done when: hosting is approved in writing and accounts are provisioned. | 2026-10-16 | 2026-10-23 | 5 | Not Started | After: Proposal walkthrough and sign-off with NDMA (P1). Needs: NDMA IT approval.
|  | Environments | Dev / test / prod environments as code | Infrastructure-as-code for all environments. | Done when: environments can be rebuilt from code. | 2026-10-26 | 2026-11-04 | 8 | Not Started | After: Hosting decision (MeghRaj / NIC / GovCloud) (H0).
|  | Delivery | CI/CD pipeline | Automated tests, builds and deployments. | Done when: every merge deploys to test automatically. | 2026-11-05 | 2026-11-11 | 5 | Not Started | After: Dev / test / prod environments as code (H1).
|  | Resilience | Backup and disaster recovery | Backups and a recovery plan — the system must stay up during disasters. | Done when: restore drill succeeds within the agreed RTO/RPO. | 2026-11-05 | 2026-11-11 | 5 | Not Started | After: Dev / test / prod environments as code (H1).
| 25. Security | Access | SSO, role-based access and audit logs | Single sign-on, role-based permissions and audit trail of every action. | Done when: all actions are attributable to a user in the audit log. | 2026-11-05 | 2026-11-12 | 6 | Not Started | After: Dev / test / prod environments as code (H1).
|  | Data Protection | Encryption and secrets management | Encrypt data at rest/in transit; keep keys in a secrets manager. | Done when: no plaintext secrets in code or config; encryption verified. | 2026-11-05 | 2026-11-10 | 4 | Not Started | After: Dev / test / prod environments as code (H1).
|  | Audit | Security audit (CERT-In empanelled auditor) | Third-party security audit before any live use. | Done when: audit passed with all high/critical findings closed. | 2027-06-03 | 2027-06-16 | 10 | Not Started | After: End-to-end integration testing (V1). Needs: auditor engagement.
| 26. MLOps | Registry | Model registry and versioning | Track every model version, data snapshot and config. | Done when: every forecast is traceable to a model version. | 2027-01-22 | 2027-01-29 | 5 | Not Started | After: Dev / test / prod environments as code (H1); Gauge-level forecaster (6/12/24/48 h) (M4).
|  | Retraining | Scheduled retraining and re-calibration | Retrain on new seasons/events and promote only if it beats the current model. | Done when: retraining runs on schedule and promotion is gated by backtest scores. | 2027-04-05 | 2027-04-14 | 8 | Not Started | After: Model registry and versioning (H6); Backtest against historical events (M11).
|  | Monitoring | Monitoring (feeds, latency, failures, drift) | Dashboards and alerts for feed staleness, forecast latency, failures and model drift. | Done when: on-call is alerted for every agreed failure mode. | 2027-02-01 | 2027-02-10 | 8 | Not Started | After: Model registry and versioning (H6); Staleness, gap and outlier rules with alerts (I22).
|  | Load | Load test for disaster-surge usage | Test with surge traffic and data volumes expected during a live event. | Done when: system meets latency targets at 3× expected peak. | 2027-05-20 | 2027-05-26 | 5 | Not Started | After: Unified SEOC command screen (F8).
I – Pilot, Validation & Rollout | 27. Testing | Integration | End-to-end integration testing | Run the full chain: feeds → forecast → twin → impact → shelters/routes → force plans. | Done when: all end-to-end test scenarios pass in the test environment. | 2027-05-20 | 2027-06-02 | 10 | Not Started | After: Unified SEOC command screen (F8); Risk and alerts panel (U5); Impact panel (U6); Shelter panel (U7); Route planning workspace (U8); Sensor and force updates in near real time (FB2); Operator verification queue for reports (FB3); Monitoring (feeds, latency, failures, drift) (H8).
|  | Tabletop | Tabletop exercise with SEOC (simulated flood) | Run a simulated flood with SEOC and DEOC staff using the dashboard. | Done when: exercise completed and issues logged and triaged. | 2027-06-03 | 2027-06-09 | 5 | Not Started | After: End-to-end integration testing (V1).
|  | UAT | User acceptance testing with NDMA / SEOC | Formal UAT against the agreed success metrics. | Done when: UAT sign-off received. | 2027-06-17 | 2027-06-30 | 10 | Not Started | After: Tabletop exercise with SEOC (simulated flood) (V2); Security audit (CERT-In empanelled auditor) (H4).
| 28. Training & Handover | Training | Operator training and SOPs | Train NDMA, SEOC and DEOC operators; write SOPs for each workflow. | Done when: all pilot operators trained and SOPs approved. | 2027-07-01 | 2027-07-12 | 8 | Not Started | After: User acceptance testing with NDMA / SEOC (V3).
|  | Documentation | Technical documentation and runbooks | Architecture, data and model docs; on-call runbooks. | Done when: runbooks tested by someone outside the build team. | 2027-07-01 | 2027-07-08 | 6 | Not Started | After: User acceptance testing with NDMA / SEOC (V3).
| 29. Shadow-Mode Pilot | Shadow Mode | Shadow run through monsoon 2027 | Run the twin alongside existing processes in the pilot district; decisions are not driven by it yet. | Done when: monsoon season run complete with forecast-vs-actual log for every event. | 2027-07-13 | 2027-09-30 | 58 | Not Started | After: Operator training and SOPs (V6); Technical documentation and runbooks (V7); Predicted vs observed side-by-side (T10); Model card and accuracy report (M12). | Covers peak monsoon (Jul–Sep 2027). Proposal requires shadow mode before the twin drives live decisions.
|  | Go / No-Go | Go / no-go review for live decision support | Review shadow-mode results with NDMA against the acceptance bar. | Done when: written go/no-go decision for live use. | 2027-10-01 | 2027-10-07 | 5 | Not Started | After: Shadow run through monsoon 2027 (V4).
| 30. Phase 2 & 3 Expansion | Phase 2 – Hazards | Landslide slope-stability model | Rainfall-threshold and slope-stability model using soil moisture sensors. | Done when: backtested on past landslides in a hill pilot district. | 2027-10-08 | 2027-11-11 | 25 | Not Started | After: Go / no-go review for live decision support (V5).
|  |  | Cyclone track and surge impact model | Use IMD cyclone tracks for wind and storm-surge impact in a coastal district. | Done when: backtested on past cyclones. | 2027-10-08 | 2027-11-11 | 25 | Not Started | After: Go / no-go review for live decision support (V5).
|  | Phase 2 – Inputs | Soil moisture and structural health sensors | Ingest soil moisture (slopes) and vibration/tilt (bridges, dams) telemetry. | Done when: sensors stream with health checks and feed the landslide model. | 2027-10-08 | 2027-10-21 | 10 | Not Started | After: Go / no-go review for live decision support (V5).
|  |  | CCTV / traffic camera water-level estimation | Computer vision on camera feeds to estimate flood depth and road conditions. | Done when: CV estimates validated against gauges at test sites. | 2027-10-08 | 2027-10-28 | 15 | Not Started | After: Go / no-go review for live decision support (V5).
|  |  | Social media monitoring with NLP filtering | Geotagged posts (X, Facebook, Instagram) filtered by NLP before being trusted. | Done when: event-detection precision meets the agreed bar on past events. | 2027-10-08 | 2027-10-28 | 15 | Not Started | After: Go / no-go review for live decision support (V5). Needs: platform API access and privacy approval.
|  |  | SACHET app ground-reporting extension | First-party ground reporting inside SACHET, feeding the same ingestion layer. | Done when: SACHET reports arrive in the ingestion layer with consent. | 2027-10-08 | 2027-10-28 | 15 | Not Started | After: Go / no-go review for live decision support (V5). Needs: NDMA / C-DOT agreement for SACHET changes.
|  | Phase 3 – Scale-up | Multi-district / state rollout plan | Onboard additional districts using lessons from the pilot; DEM and sensor gap analysis per district. | Done when: rollout plan with district order, data gaps and costs approved. | 2027-11-12 | 2027-12-02 | 15 | Not Started | After: Landslide slope-stability model (X1); Cyclone track and surge impact model (X2).
Formulas:
Working days = NETWORKDAYS([Start],[End],Holidays!$A2:A40)

## Summary
Summary by Module
All figures are formulas over the Tracker tab; they update as Status and dates change.
Module | Sub tasks | Done | In Progress | Not Started | Blocked | % Done | Start | End | Working days
A – Programme Setup & Governance | 16 | 1 | 0 | 15 | 0 | 6.25% | 2026-09-21 | 2026-12-04 | 54
B – Unified Data Ingestion (Layer 1) | 18 | 0 | 0 | 18 | 0 | 0% | 2026-10-29 | 2026-12-23 | 40
C – AI/ML Prediction Engine (Layer 2) | 12 | 0 | 0 | 12 | 0 | 0% | 2026-12-04 | 2027-04-08 | 87
D – Digital Twin Simulation (Layer 3) | 10 | 0 | 0 | 10 | 0 | 0% | 2026-10-29 | 2027-04-30 | 129
E – Planning & Decision Support (Layer 4) | 14 | 0 | 0 | 14 | 0 | 0% | 2027-03-11 | 2027-05-10 | 42
F – Force Coordination & Control (Layer 5) | 8 | 0 | 0 | 8 | 0 | 0% | 2026-11-27 | 2027-05-19 | 121
G – Command Dashboard & Feedback Loop | 13 | 0 | 0 | 13 | 0 | 0% | 2026-10-27 | 2027-05-18 | 143
H – Platform, Security & MLOps | 11 | 0 | 0 | 11 | 0 | 0% | 2026-10-16 | 2027-06-16 | 170
I – Pilot, Validation & Rollout | 14 | 0 | 0 | 14 | 0 | 0% | 2027-05-20 | 2027-12-02 | 141
Total | 116 | 1 | 0 | 115 | 0 | 0.8621% | 2026-09-21 | 2027-12-02 | 310
Key milestones
Milestone | Tracker row | Target date
NDMA sign-off on proposal | 5 | 2026-10-15
Pilot district selected | 6 | 2026-10-23
Core agency feeds live (IMD, CWC) | 25 | 2026-12-03
Flood forecast backtest passed | 48 | 2027-04-02
Digital twin animates forecast | 55 | 2027-04-12
Unified SEOC command screen | 81 | 2027-05-19
End-to-end integration test | 106 | 2027-06-02
UAT sign-off | 108 | 2027-06-30
Shadow mode complete (monsoon 2027) | 111 | 2027-09-30
Go / no-go for live use | 112 | 2027-10-07
Phase 3 rollout plan approved | 119 | 2027-12-02
Formulas:
Start = MIN(H4:[Start, row above])
End = MAX(I4:[End, row above])
Working days = NETWORKDAYS([Start],[End],Holidays!$A2:A40)

## Decisions & Dependencies
External Decisions & Dependencies
Everything the team needs from NDMA or another agency. 'Needed by' = start of the first task that waits on it (linked to the Tracker).
# | Decision / dependency | Owner | Blocks | Needed by | Status | Notes
1 | Proposal walkthrough and sign-off | NDMA | Proposal walkthrough and sign-off with NDMA (P1) | 2026-10-12 | Open
2 | Nomination of candidate pilot districts | NDMA / State SDMA | Select Phase 1 pilot district (P2) | 2026-10-16 | Open | Prefer a well-mapped, flood-prone district (terrain-resolution risk).
3 | Hosting / cloud approval (data residency in India) | NDMA IT | Hosting decision (MeghRaj / NIC / GovCloud) (H0) | 2026-10-16 | Open | Blocks all environments.
4 | IMD data-sharing agreement | IMD | IMD data-sharing agreement (D1) | 2026-10-26 | Open | Formal agreements from day one (inter-agency risk).
5 | CWC data-sharing agreement | CWC | CWC data-sharing agreement (D2) | 2026-10-26 | Open
6 | ISRO / NRSC imagery access | NRSC | ISRO / NRSC satellite data access (D3) | 2026-10-26 | Open
7 | Survey of India DEM licence | Survey of India | Survey of India high-resolution DEM licence (D4) | 2026-10-26 | Open
8 | Google Maps Platform budget | NDMA Finance | Google Maps Platform licence and billing (D6) | 2026-10-16 | Open
9 | Commercial imagery procurement | NDMA Procurement | Commercial high-resolution imagery procurement (D7) | 2026-10-26 | Open | Phase 1 pilot district only.
10 | Privacy policy legal review (DPDP Act 2023) | NDMA Legal | Data governance and privacy policy (G1) | 2026-10-16 | Open
11 | IDRN inventory access | NDMA / NIDM | IDRN resource inventory import (I13) | 2026-11-20 | Open
12 | Pilot sensor feed access | State water resources dept / vendor | River / rain gauge sensor telemetry (pilot) (I14) | 2026-11-24 | Open
13 | WhatsApp Business API account | NDMA | WhatsApp ground-reporting bot (I17) | 2026-11-24 | Open
14 | NDRF / SDRF unit data and tracking feed | NDRF / SDRF | NDRF / SDRF unit and capability registry (F1); GPS / radio tracking integration (F2) | 2026-11-27 | Open
15 | SACHET / Cell Broadcast export format | NDMA / C-DOT | Export route and shelter plans for official channels (E14) | 2027-04-30 | Open | Operators issue messages; system never auto-sends.
16 | Security auditor engagement | NDMA IT | Security audit (CERT-In empanelled auditor) (H4) | 2027-06-03 | Open | CERT-In empanelled.

## Risks
Risk Register
Risks 1–5 from proposal section 7; 6–8 added for delivery. Impact / Likelihood are initial team estimates — review with NDMA.
# | Risk | Impact | Likelihood | Mitigation | Linked tasks | Status
1 | Terrain data resolution — inconsistent elevation data distorts hazard-flow predictions. | High | Medium | Launch Phase 1 in a single well-mapped pilot district before scaling. | P2, D4, I9 | Open
2 | Crowdsourced data reliability — misinformation or false reports corrupt the model. | High | High | Strict NLP/verification filtering and trust scores before ingestion; operator review queue. | I20, FB3, X5 | Open
3 | Model trust & validation — wrong predictions misdirect forces or plans. | High | Medium | Backtest against historical data and run in shadow mode before live decisions. | M11, T9, T10, V4, V5 | Open
4 | Data privacy & consent — citizen location and social data create legal liability. | High | Medium | Data-governance and privacy policy built alongside the technical build; consent on every report. | G1, G2, G3 | Open
5 | Inter-agency coordination — IMD, CWC, ISRO use siloed, incompatible formats. | High | High | Formal data-sharing agreements and a common schema from day one. | D1, D2, D3, I1 | Open
6 | Agreement delays push the schedule (agency approvals are outside team control). | High | High | Start agreements immediately after pilot selection; build on open data (Copernicus, OSM) meanwhile. | D1–D7, I8 | Open
7 | Shadow-mode window depends on monsoon timing; a quiet season gives few events. | Medium | Medium | Supplement with historical replays; extend shadow mode or add a second pilot basin if needed. | V4, T9 | Open
8 | System unavailable during a live disaster (surge load, outages). | High | Low | Load testing at 3× peak, DR drill and low-bandwidth mode. | H9, H10, U10 | Open

## Holidays
Date | Holiday | Edit this list to match the NDMA gazetted holiday calendar; Working days on every tab uses A2:A40. The planned dates on the Tracker were scheduled with this list.
2026-10-20 | Dussehra
2026-12-25 | Christmas
2027-01-26 | Republic Day
2027-03-26 | Good Friday